## AHS
Albany High School
SIG Monitoring Cover Sheet
Monitoring Period:
Progress Score |  |  |  |  | Quality Score
3 = A lot of evidence exists that identified activities are underway |  |  |  |  | 3 = Activities are mostly being implemented
2 = Some evidence exists that identified activities are underway |  |  |  |  | 2 = Activities are generally being implemented according to the action Plan
1 = Little to no evidence exists that identified activities are underway |  |  |  |  | 1 = Action Plan needs more development
0 = No evidence |  |  |  |  | 0= Activities are NOT being implemented according to the action plan
1. Developing and increasing teacher and school leader effectiveness
SIG Indicator | Subcommittee | BLT liaison | Progress | Quality | Expectations | Evidence, Feedback and Next Steps
1a: School Leader (Principal) Effectiveness |  |  | 2 | 2 | CASDA- leadership Training Seminar and ongoing Principal's PLC | CASDA, CSSR - Coaches monitoring Dr. McCalla's progress 5 days APR training August 2011, Teacher PD on APPR
CSSR - services relating to the coordination of AHS strategies for implementing Transformation Model
Dr. McCalla and academy principals attend National Institute for Urban School
District will monitor Dr. McCalla's effectiveness
1b: Evaluation System | APPR PD Committee SED Mandates | D.Getto | 3 | 3 | Action Research training Regents week | APPR - Continual review of process PD Committee to include development of review of data on student growth
PD relating to new APPR
Administration and Teachers participate in 4-day Teacher institute by Teaching and Learning Solutions
Evaluation Site Coordinator (stipend position)
Evaluator Academy - week long PD series held by Teaching and Learning Solutions
Eight day train the Trainer Session
Trainers become turnkey Trainers - training other AHS teachers (Faculty meetings
Consultant Teacher/Evaluator hired and trained as PAR
New APPR agreement for Teachers and Administration
1c: Identify & Reward | District office and Academy Administration | D.Getto | 2 | 2 | New Contractual Agreements including rewards | Comply with SED Mandates Perfect Attendance Certificates Recognition Board
1d: Identify & Remove | Academy Administration | Harper/ Mc Calla | 1 | 1 | New contractual agreement including process for a TIP plan | Negotiations relating to the 20% locally defined
1e: On-going, high quality, job- embedded PD | PD Committee | C. Wilson D. Getto | 3 | 2 | CSSR, CASDA BLT training, PD Committee, Common planning time(PLC), RTTT, faculty meeting, Math and ELA Coaches, Action Research | Need more development in exit tickets and survey of effective after PD occurs, See PD committee notes
CSSR and CASDA - Partner meeting each fall and spring to monitor implementation
CSSR - training and support BLT
Establish building level PD committee
Hire ELA and Math Coaches
168 minutes of Common Planning Time built into master schedule
PD during mandatory, monthly all faculty meetings and in PLC
Coaching - one to one and small group in classroom and PLC
1f: Promotion& Career Growth |  | R. Floess | 1 | 1 | Take One! National Board first step towards National Board, district pay all expenses of mandatory PD | How many people are currently participating in Take One and how many in process for national board
1g: System for measuring Changes in instructional Practices | PD Committee | C. Wilson D. Getto | 1 need tool | 1 | Poll everywhere, CASDA, mechanism to provide feedback: effective & relevancy of PD sessions | Monthly collaborative PD - department Data review to drive instruction Develop tools/process to measure PD effectiveness
Leaders participate in PD with teachers to better support, supervise and assess teachers' utilization of information and strategies learned
CASDA - work with Principals PLC to create a system to measure changes in instructional practices resulting from PD and coaching
Provide teachers with mechanism to provide feedback on PD
1h: Hiring policies and procedures | Academy Administration | Dr. McCalla | 0 | 0 | Involuntary transfers, frequent interval changes during school year | Develop protocol for changes
2. Comprehensive instructional Reform Strategies
SIG Indicator | Subcommittee | BLT liaison | Score | Quality | Expectations | Evidence, Feedback and Next Steps
2a: Use data to identify and implement an instructional program | BLT | Mc Calla, Karp | 2 | 1 | Pearson Inform | AHS Inquiry Team, 90-90-90 protocols for Data Team
2b: Continuous use of Student Data to inform and differentiate instruction | Inquiry Team | Dale Getto | 2 | 1 | Transformation Officer, CASDA, RTTT, COMPASS training, Instructional Supervisors and Coaches for PD, Teachers use data to identify and implement targeted instruction, formative and summative assessments | Workshops with departments with variances ASAP analysis report to BLT
Atlas mapping, Instructional Supervisors and coaches review, "look-for" rubric to assess teachers' alignment and implementation (CASDA)
CASDA- help district to adopt a standardized, formal system of data protocols in a two day Institute for COMPASS
Instructional Supervisors and Coaches provide embedded PD to teachers on how to utilize the data to drive decisions and inform instruction
Teachers in PLC - utilize student data to identify and implement targeted instruction, implement continuous use of student data to inform and differentiate instruction
District, building and teacher teams - Review Formative and summative assessments
2c: Periodic reviews of curriculum for fidelity and impact | BLT |  | 2 | 1 | Atlas mapping, Instructional Supervisors and coaches review, "look-for" rubric to assess teachers' alignment and implementation (CASDA) | Walk through, APPR, Working on Midterm, Continual process, 90-90-90 protocols for creating rigorous curriculum, common. Asses…
CASDA - pilot use of Atlas Curriculum Mapping Software
Instructional Supervisors and Coaches - conduct periodic reviews of maps through PLC and monthly department meetings
Building leaders, Instructional Supervisors and Consultant Teacher/Evaluator will use "look-for" rubrics to assess individual teachers' alignment and implementation of instruction
2d: RtI | RtI | Wilson | 2 | 2 | IST is now RtI | RtI comm. w/ purpose, notes, outcome RtI plan
Establish building level RtI team
RtI team meets monthly to research and review resources and best practices
Identification of universal screening tool and Tier I, II and III Interventions
PD on RtI plan and capacity to begin implementation for 2012 (all building level administrators , coaches and teachers)
2e: Effective strategies for SWD/LEP | ESL Task Force | Haertel | 2 | 2 | ESL Sheltered Instructional Program SIOP training, Wilson Lang. Intervention Model , PLC, ESL afterschool program | SIOP PD in March, ESLAP, PLC development
Implement ESL Sheltered Instruction Program (grades 11 and 12) for students eligible for Regents exams in SS and ELA
Two ESL teachers and Two core content area teachers will participate in SIOP training
ESL teachers will participate and begin to use in Wilson Language Intervention Model
Special Education and ESL teachers will participate in PLC for common planning time and vertical meetings with other teachers. In PLC's, all teachers will learn strategies for co-teaching
ESL Afterschool Program will expand to include monthly weekend field trips
2f: Integrating technology-based supports and interventions | Tech Comm./ELO Comm. |  | 3 | 2 | CASDA, SCALE, Tech specialist, TPACK PD, APEX, Saturday Academies, | Assess effectiveness of APEX programs, put APEX ELOP into print/brochure
Expand SCALE - student centered Active Learning Environments through ARRA grant
[5 empty] | Hire Technology Specialist - oversight of set up of SCALE classrooms and technical support | Don Frangello,
Training for Core content area teachers using TPACK PD model
Equip each SCALE classroom will digital communication tools including smart board, document camera, student response system and cart of netbooks
More smart boards purchased throughout building and licenses for Smart Notebook Math tools and Adobe Creative Suite Software
APEX for credit unit recovery; to build foundation skills and participate in advanced courses. AIS for 9th and 10th graders ELA and math, 9th grade Saturday Academies, Afterschool Senior Academy, AP Language course credit
APEX will train on-site tutors( AHS teachers) to students
2g: Increasing rigor via Advanced coursework | BLT |  | 2 | 2 | College board/springboard, IBO, AP, IB, Career & Tech Ed | Train Teachers and provide student supports
Four Themed Academies create
Each Academy offers students opportunities to earn college credits via AP and IB dual-enrollment courses. Training in SpringBoard AP, Level I IB and Content Area AP and Level II IB
Each Academy offers CTE and exploration programs
Utilize APEX as explained previously
2h: Improving Transition from MS to HS | BLT | Harper | 2 | 2 | Summer Transition Camp, thematic Summer Camp, AP Honors camp, Freshman Seminar | Create BLT sub-committee Start planning for 2012-13 (Stan Harper 1/25/12 mtg)
Summer Transition Camp
Thematic Summer Camp and AP Summer Camp
Freshman Seminar - bimonthly workshop throughout school year. Each core content area team will utilize one class period per month to teach study skills, time management and organizational skills
2i: Increase graduation rates | Inquiry Team | Getto | 2 | 2 | Naviance, AVID (50 students 2011-12), AVID coordinator/teacher/PD | expose more staff to programs and opportunities for students, guidance news letter
Two counselors assigned to each academy
CASDA provide counselors with PD on use of NYS Comprehensive Counseling Program
Counselors use Naviance Succeed Software
Implement AVID program phased in 50- 9th graders in 2011-12
AVID Coordinator and site team established
Hire AVID teacher in 11-12
AVID institute to effectively implement
Site team will recruit students to participate
Utilization of APEX
2j: Early warning systems | Attendance Sub. Comm. | Bennett | 2 | 2 | 5 week interval grades ACTION meetings and follow up , Back to School Attendance Intervention Program (HSC) summer outreach, track student attendance, Community intervention meeting
Review o f5 week interval grades (Counselors and BLT ) to identify students who are failing to achieve
Counselors and principals will coordinate and facilitate action meetings with students/parents/advisor/teachers and principal
Back to School Attendance Intervention Program for incoming 9th grade students for students identified as having a history of problematic attendance
School Attendance Officer and Home School coordinator and partners will describe the roles and responsibilities of each in implementing programs
District will assign up to 25 students to each academy's HSC. Conduct summer outreach visits to homes
HSC will track student attendance .. Visit home and neighborhood watch
Community Intervention Meeting
3. Increasing learning time and creating community-orientated schools
SIG Indicator | Subcommittee | BLT liaison | Progress | Quality | Expectations | Evidence, Feedback and Next Steps
3a: Increased Learning time | School Climate and Culture Committee | Bennet | 3 | 2 | 2 instructional days to school year | Some limitations due to scheduling difficulties Work to improve teaming schedule
APEX
3b: Family and Community Engagement | School Climate and Culture Committee | Getto | 3 | 1 | Family Engagement Coordinator | Position moved to Purchased Services
3c:Create Safe School environments | School Climate and Culture Committee | Bennet | 3 | 1 | Climate and Culture Inventory (CSCI), Parent-Teacher-Student Association and Family Engagement Coordinator, CASDA | First inventory completed, Focus groups created
Culture and Climate Committee will work with Falcon council to administer Comprehensive School Climate Survey
After survey CASDA will provide Team Development Training, Survey Review and Action Plan training
District will develop partnerships with parent through PTSA and Family Engagement Coordinator. (Increase FTE of Coordinator.
Expand existing 9th grade A-Plus mental Health Clinic by hiring an additional Social Worker
3d: Advisory Periods | Advisory | Schaedwell | 0 | 0 | Student Advisory Program, training CSSR @ Dec. partner meeting activity moved to SLC. | Contractual issues and scheduling issues are impeding progress. Need to explore models and consult with CSSR
CSSR - work with team of administrators, teachers and student s to create a purposeful Student Advisory Program
Training for Advisors
Master schedule has advisory period built in for 2012
3e: Approaches to improve school climate and discipline | Attendance/Behavior | Melanie | 2 | 1 | National Coalition Building Institute PD, CASDA, CSSR, Positive Behavioral System, new governance structure | NCBI training, new homework initiative going into place
Contract with National Coalition Building Institute to take steps to eliminate bullying and student harassment. Training for students, families, staff and community partners
Albany High Diversity Resource team trained and establish train the trainer by 2013-14
CASDA will provide technical assistance and mentoring on Positive behavioral System
Personalization of the school environment ( governance structure, student advisory, )
4. Providing operational flexibility and sustained support
SIG Indicator | Subcommittee | BLT liaison | Progress | Quality | Expectations | Evidence, Feedback and Next Steps
4a: Operational Flexibility | Academy Park |  | 3 | 2 | 4 theme academies, SIM, | Dale hired
4b: Technical assistance and related support | Academy Park |  | 3 | 2 | NYSED title 1 school and Community services team, CSSR, CASDA, Transformation Officer | transformation officer hired
Establish Office for School Redesign - provided technical assistance and related support - Transformation officer focus on improving student achievement
Technical assistance from NYSED Title I school and community services team
CSSR and CASDA provide educational consultant services for implementing transformation model at AHS
4c: New governance arrangement | Academy Park |  | 3 | 1 | Office for School Redesign and four academies | Academies in place, refining themes
4d: External Partners | Academy Park |  | 1 | 1 | Recruit, screen and select external partners | Need to develop protocol to evaluate success of partners' work (Eileen Leffler)
Committees that Report to BLT:
Inquiry | Math & ELA Coaches | Grading | AVID |  | Themed coordinators SLC | Culture& Climate
Building Curriculum | Night School | ELOP | ESL Task Force |  | Falcon Council | Attendance and Behavior